## Stakeholders
Role | Name(s) | Responsibility
Lead | Mohammed Tobacco Noor, Venkata Maddu, Mayank Patel | Drive execution & approvals
PO |  | Business ownership
BA | Laxmi Koneru, Omkumar Subramanian | Requirement validation
DevOps / Infra |  | Environment setup & deployment
App Owners |  | Validate integration post-migration

## Environment Mapping
Environment | Current Domain | New Domain | Target Timeline | Owner
DEV | crdp-dev.bankofamerica.com | erdp-dev.bankofamerica.com
SIT | crdp-sit.bankofamerica.com | erdp-sit.bankofamerica.com
UAT | crdp-uat.bankofamerica.com | erdp-uat.bankofamerica.com
PROD | crdp.bankofamerica.com | erdp.bankofamerica.com

## Migration Steps
Step | Task | Owner | Dependency | Status
1 | Request new domain (DEV first) | Infra team | N/A | Pending
2 | Request new TOKEN ID setup | Security/SSO team | Step 1 | Pending
3 | Update container with new domain + cert | DevOps | Step 2 | Pending
4 | Deploy application (DEV) | App Team | Step 3 | Pending
5 | Integration testing with consumers | QA + App Owners | Step 4 | Pending
6 | Rollout to SIT, UAT, PROD | All teams | DEV validation | Pending

## Risks & Mitigation
Risk | Impact | Mitigation
Consumer apps not updated with new domain | Service outages | Early communication + parallel run for 2 weeks
Certs not in sync | Deployment failure | Pre-validate with DevOps
Timeline slippage | Delay in rebrand | Buffer in SIT/UAT timeline

## Timeline
Week | Activity | Environment | Owner | Notes
Week 1 | DEV migration | DEV
Week 2 | SIT migration | SIT
Week 3 | UAT migration | UAT
Week 4 | PROD migration | PROD